## Trang tính1
|  | Type | Status | Timeline | Members | Notes
| Database |  | Done | 2022-06-19 | GROUP
| SRS |  | Done(19/6) | 2022-06-15 | GROUP
Admin
1 | Login by Username, Password | Back-end | In progress |  | Nguyễn Khoa Thiên Long
| Login | Front - end |  |  | Trần Minh Huy
2 | Logout | Back-end |  |  | Nguyễn Khoa Thiên Long
| Admin | Front - end | In progress |  | Trần Minh Huy
3 | View Order (Accept, Decline) | Back-end |  |  | Nguyễn Hoàng Kha
| Admin | Front - end | In progress |  | Trần Minh Huy
4 | Delete - Insert - Update Product | Back-end |  |  | Đinh Thế Khang
| Add product | Front - end |  |  | Đặng Quang Trung
| Update product | Front - end | In progress |  | Đặng Quang Trung
5 | View List Product | Back-end | In progress |  | Đinh Thế Khang
| Admin | Front - end | In progress |  | Trần Minh Huy
6 | View List Category | Back-end |  |  | Đinh Thế Khang
| Admin | Front - end | In progress |  | Trần Minh Huy
7 | Delete - Insert - Update Category | Back-end |  |  | Đinh Thế Khang
| Add category | Front - end |  |  | Đặng Quang Trung
| Update category | Front - end |  |  | Đặng Quang Trung
8 | Edit promotion | Back-end |  |  | Nguyễn Hoàng Kha
| Admin | Front - end | In progress |  | Trần Minh Huy
Customer
9 | View product - HomePage | Back-end | In progress |  | Nguyễn Hoàng Kha
| Home | Front - end | In progress |  | Nguyễn Mạnh Lực
10 | View Product By Category | Back-end |  |  | Nguyễn Hoàng Kha
| Home view product | Front - end |  |  | Nguyễn Mạnh Lực
11 | View details product | Back-end |  |  | Nguyễn Khoa Thiên Long
| View details product | Front - end |  |  | Nguyễn Mạnh Lực
12 | View list product by name - Search | Back-end |  |  | Nguyễn Khoa Thiên Long
| View list product by name - Search | Front - end |  |  | Nguyễn Mạnh Lực
13 | View list product by location | Back-end |  |  | Nguyễn Thanh Tùng
| Home view product | Front - end |  |  | Nguyễn Mạnh Lực
14 | Look up purchase history information | Back-end |  |  | Nguyễn Khoa Thiên Long
| Look up purchase history information | Front - end |  |  | Trần Minh Huy
15 | View Cart | Front - end | In progress |  | Nguyễn Thanh Tùng
16 | Delete - Update product in cart | Front - end |  |  | Đinh Thế Khang
17 | Add to Cart | Front - end |  |  | Nguyễn Thanh Tùng
18 | Check out | Back-end |  |  | Nguyễn Thanh Tùng
| Check out | Front - end |  |  | Trần Minh Huy
19 | Update Customer delivery Information | Back-end |  |  | Nguyễn Thanh Tùng
| Update Customer delivery Information | Front - end |  |  | Đặng Quang Trung
20 | Logout | Back-end |  |  | Nguyễn Khoa Thiên Long
| Update Customer delivery Information | Front - end |  |  | Đặng Quang Trung
21 | Filter Product | Back-end |  |  | Nguyễn Hoàng Kha
| Home view product | Front - end |  |  | Nguyễn Mạnh Lực
22 | View Promotion | Back-end |  |  | Nguyễn Hoàng Kha
| View cart | Front - end |  |  | Trần Minh Huy
Hoàn tất |  | 2022-07-24

## Trang tính2
-Product: id, name, price, quantity, description, detail(), productInformation(), condition.
-Detail: monitor(), camera(), operating system & CPU()
, memory & storage(), connect(), battery()
, utilities(), general information().
-Category: id, name.
-Promotion: proId, %discount or price discount, condition, status, date.
-Order:
-OrderDetails: